## Summary
Weekly SIT Status Report
Report Date: | 07/29/2026 | Reporting Period: | 61 | Forecast Period: | 39
KEY METRICS
Metric | Value
Total Planned | {{TotalPlanned}}
Total Executed | {{TotalExecuted}}
Total Passed | {{TotalPassed}}
Total Failed | {{TotalFailed}}
Pass Rate | {{PassRate}}
Not Started | {{TotalNotStarted}}
In Progress | {{TotalInProgress}}
AI SUMMARY
{{AISummary}}
Tokens in {{ }} are replaced automatically. Add charts below referencing the "By Workstream" and "Sub-Suites" sheets.

## By Workstream
Workstream | Planned | Executed | Passed | Failed | Not Started | In Progress | Blocked | Pass %
PDM | 83 | 63 | 20 | 43 | 19 | 0 | 1 | 32%
Benefits | 446 | 65 | 59 | 6 | 381 | 0 | 0 | 91%
Enrollment | 21 | 0 | 0 | 0 | 21 | 0 | 0 | 0%
EDI | 22 | 1 | 0 | 1 | 21 | 0 | 0 | 0%
TOTAL | 572 | 129 | 79 | 50 | 442 | 0 | 1 | 61%

## Sub-Suites
Suite | Planned | Executed | Passed | Failed | Not Started | In Progress | Blocked | Pass %
PDM
SIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
E2E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Iteration 2 | 83 | 63 | 20 | 43 | 19 | 0 | 1 | 32%
Iteration 2.1 | 39 | 19 | 7 | 12 | 19 | 0 | 1 | 37%
CPIMS | 16 | 10 | 7 | 3 | 6 | 0 | 0 | 70%
CPIMS-Prac | 10 | 10 | 7 | 3 | 0 | 0 | 0 | 70%
CPIMS-Org | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0%
CPIMS-Prac Role | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Ancillary | 9 | 9 | 0 | 9 | 0 | 0 | 0 | 0%
Rosters | 14 | 0 | 0 | 0 | 13 | 0 | 1 | 0%
MT Carmel | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0%
Mercy | 5 | 0 | 0 | 0 | 4 | 0 | 1 | 0%
Toleda Clinic | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0%
Kettering | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0%
Iteration 2.0 | 44 | 44 | 13 | 31 | 0 | 0 | 0 | 30%
CPIMS | 24 | 24 | 7 | 17 | 0 | 0 | 0 | 29%
CPIMS-Prac | 10 | 10 | 5 | 5 | 0 | 0 | 0 | 50%
CPIMS-Org | 6 | 6 | 2 | 4 | 0 | 0 | 0 | 33%
CPIMS-Prac Role | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0%
Ancilliary | 9 | 9 | 4 | 5 | 0 | 0 | 0 | 44%
Rosters | 11 | 11 | 2 | 9 | 0 | 0 | 0 | 18%
Mercy | 5 | 5 | 2 | 3 | 0 | 0 | 0 | 40%
Toledo Clinic | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0%
Kettering | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0%
Iteration 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Benefits
Signature HMO | 200 | 19 | 18 | 1 | 181 | 0 | 0 | 95%
Access PPO (Premium PPO INN) | 155 | 1 | 0 | 1 | 154 | 0 | 0 | 0%
Premium PPO | 82 | 45 | 41 | 4 | 37 | 0 | 0 | 91%
Enrollment
UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
E2E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
SIT | 21 | 0 | 0 | 0 | 21 | 0 | 0 | 0%
PERF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
EDI
UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
E2E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
SIT | 22 | 1 | 0 | 1 | 21 | 0 | 0 | 0%

## Bug Analysis
bugsBySeverity
Value | Count | %
3 - Medium | 30 | 77%
2 - High | 7 | 18%
1 - Critical | 2 | 5%
bugsByPriority
Value | Count | %
2 | 37 | 95%
3 | 2 | 5%
Priority 1 | 5 | 14%
Priority 2 | 15 | 41%
Priority 3 | 12 | 32%
Priority 4 | 5 | 13%
TOTAL | 37 | 100%
↑ The extension replaces this data on each run based on your configured groupByFields.

## Charts Guide
How to Add Charts to This Template
After the extension populates data on each run, add charts once and they will auto-update:
RECOMMENDED CHARTS
Sheet "By Workstream":
1. Select A1:H5 (headers + 4 workstream rows)
2. Insert → Charts → Clustered Bar (shows Planned/Executed/Passed/Failed/Blocked side by side)
3. Or select A1:A5 + I1:I5 for a Pass Rate bar chart per workstream
Sheet "Sub-Suites":
1. Select the rows for one workstream block
2. Insert → Stacked Bar to show depth breakdown
Sheet "Bug Analysis":
1. Select Value + Count columns in any section (e.g. A3:B6)
2. Insert → Pie or Donut chart for severity/priority distribution
TOKENS (replaced each run on the Summary sheet)
07/29/2026 — report date (from Variables tab)
61 — reporting period
39 — forecast period
{{TotalPlanned}} — consolidated planned test count
{{TotalExecuted}} — consolidated executed test count
{{TotalPassed}} — consolidated passed test count
{{TotalFailed}} — consolidated failed test count
{{PassRate}} — overall pass rate %
{{TotalNotStarted}} — consolidated not-started count
{{TotalInProgress}} — consolidated in-progress count
{{AISummary}} — AI-generated executive summary (if ai-summary extension enabled)
Add any custom {{TOKEN}} to the Summary sheet and map it in the Variables tab.
TIP: Set EXCEL_TEMPLATE in your .env (or Credentials tab) to point to a customized copy.