## Summary
Weekly SIT Status Report
Report Date: | {{Date}} | Reporting Period: | {{PP}} | Forecast Period: | {{FP}}
KEY METRICS
Metric | Value
Total Planned | {{TotalPlanned}}
Total Executed | {{TotalExecuted}}
Total Passed | {{TotalPassed}}
Total Failed | {{TotalFailed}}
Pass Rate | {{PassRate}}
Not Started | {{TotalNotStarted}}
In Progress | {{TotalInProgress}}
AI SUMMARY
{{AISummary}}
Tokens in {{ }} are replaced automatically. Add charts below referencing the "By Workstream" and "Sub-Suites" sheets.

## By Workstream
Workstream | Planned | Executed | Passed | Failed | Not Started | In Progress | Blocked | Pass %
PDM | 120 | 95 | 80 | 15 | 20 | 0 | 5 | 84%
Benefits | 85 | 70 | 65 | 5 | 15 | 0 | 0 | 93%
Enrollment | 100 | 88 | 75 | 13 | 12 | 0 | 0 | 85%
EDI | 60 | 45 | 40 | 5 | 13 | 0 | 2 | 89%
TOTAL | 365 | 298 | 260 | 38 | 60 | 0 | 7 | 87%
↑ Add charts referencing rows 2:5 of this sheet. The extension overwrites this data on each run.

## Sub-Suites
Suite | Planned | Executed | Passed | Failed | Not Started | In Progress | Blocked | Pass %
PDM
Iteration 2 | 120 | 95 | 80 | 15 | 20 | 0 | 5 | 84%
Iteration 2.1 | 60 | 48 | 42 | 6 | 10 | 0 | 2 | 88%
CPIMs | 30 | 24 | 22 | 2 | 5 | 0 | 1 | 92%
Phase 1 | 15 | 12 | 11 | 1 | 2 | 0 | 1 | 92%
↑ The extension replaces this data on each run, grouped by workstream.

## Bug Analysis
bugsBySeverity
Value | Count | %
1 - Critical | 3 | 8%
2 - High | 12 | 32%
3 - Medium | 18 | 49%
4 - Low | 4 | 11%
TOTAL | 37 | 100%
bugsByPriority
Value | Count | %
Priority 1 | 5 | 14%
Priority 2 | 15 | 41%
Priority 3 | 12 | 32%
Priority 4 | 5 | 13%
TOTAL | 37 | 100%
↑ The extension replaces this data on each run based on your configured groupByFields.

## Charts Guide
How to Add Charts to This Template
After the extension populates data on each run, add charts once and they will auto-update:
RECOMMENDED CHARTS
Sheet "By Workstream":
1. Select A1:H5 (headers + 4 workstream rows)
2. Insert → Charts → Clustered Bar (shows Planned/Executed/Passed/Failed/Blocked side by side)
3. Or select A1:A5 + I1:I5 for a Pass Rate bar chart per workstream
Sheet "Sub-Suites":
1. Select the rows for one workstream block
2. Insert → Stacked Bar to show depth breakdown
Sheet "Bug Analysis":
1. Select Value + Count columns in any section (e.g. A3:B6)
2. Insert → Pie or Donut chart for severity/priority distribution
TOKENS (replaced each run on the Summary sheet)
{{Date}} — report date (from Variables tab)
{{PP}} — reporting period
{{FP}} — forecast period
{{TotalPlanned}} — consolidated planned test count
{{TotalExecuted}} — consolidated executed test count
{{TotalPassed}} — consolidated passed test count
{{TotalFailed}} — consolidated failed test count
{{PassRate}} — overall pass rate %
{{TotalNotStarted}} — consolidated not-started count
{{TotalInProgress}} — consolidated in-progress count
{{AISummary}} — AI-generated executive summary (if ai-summary extension enabled)
Add any custom {{TOKEN}} to the Summary sheet and map it in the Variables tab.
TIP: Set EXCEL_TEMPLATE in your .env (or Credentials tab) to point to a customized copy.