## Slide 1: MMO Test Execution & Bug Report
07/21/2026

## Slide 2
581*
Total Test Cases
55
Passed (63%)
33
Failed (38%)
32
Open Bugs
Status
Executive Summary:
Overall, SIT execution status is on track. Benefits SIT has begun and continues to make progress per plan.
PDM ancillary Iteration #2, round 1 execution has completed, and retest is pending bug fixes/closure.
Preliminary testing for Enrollment and EDI has begun and is on-track to kickstart.
Bug Triage:
32 open bugs remain in “New” and “Active” state. Critical and High priority bugs have been triaged and owners are identified.
SIT Execution Status Report | Executive Summary
As-of: 07/21/2026
*Test case planning is still in progress; expect planned test case count to increase in coming weeks
88
Executed
Test Case and Bug Breakdown
Review Summary |  |  |  |  | 
Workstreams | Planned TC’s* | Executed | Passed | Failed | Open Bugs
PDM Iteration #2 | 47 | 44 | 13 | 31 | 25
Benefits | 491 | 43 | 42 | 1 | 1
Enrollment | 21 | 0 | 0 | 0 | 2
EDI | 22 | 1 | 0 | 1 | 4
Grand Total | 581 | 88 | 55 | 33 | 32
Legend:
Complete
On Track
At Risk
Off Track
Overall Status:
Executed — The test case has been run at least once; a result has been recorded (regardless of outcome).
Passed — The test case was executed and all steps/assertions met the expected results successfully.
Failed — The test case was executed but one or more steps/assertions did not match the expected results, indicating a bug or issue.
In Progress – The test case is currently being run by a tester and is not completed yet.
Not Started – The test case has not been run yet.
Notes: Total > Executed > In Progress> Pass > Fail > Defect

## Slide 3
Testing Execution Report | All Work Streams
As-of: 07/21/2026
Workstream Test Execution Summary |  |  |  |  |  |  |  |  |  |  | 
Data Sources | Phase | Status | Execution Start Date | Target Completion Date** | Planned TCs* | Executed | Not Started | In Progress | Passed | Failed | Bugs
PDM | Iteration 2 |  | 5/1/2026 | 6/30/2026 7/31/2026 | 47 | 44 | 3 | 0 | 13 | 31 | 25
Benefits | SIT |  | 6/22/2026 | 10/15/2026 | 491 | 43 | 448 | 0 | 42 | 1 | 1
Enrollment | SIT |  | 7/15/2026 | 10/15/2026 | 21 | 0 | 21 | 0 | 0 | 0 | 2
EDI | SIT |  | 7/10/2026 | 10/15/2026 | 22 | 1 | 21 | 0 | 0 | 1 | 4
Grand Total | -- | -- | -- | -- | 581 | 88 | 493 | 0 | 55 | 33 | 32
*Test case planning is still in progress; expect planned test case count to increase in coming weeks
**To be discussed with MMO/HE
Executed — The test case has been run at least once; a result has been recorded (regardless of outcome).
Passed — The test case was executed and all steps/assertions met the expected results successfully.
Failed — The test case was executed but one or more steps/assertions did not match the expected results, indicating a bug or issue.
In Progress – The test case is currently being run by a tester and is not completed yet.
Not Started – The test case has not been run yet.
Overall Testing Execution Summary |  |  |  |  |  | 
Planned TCs* | Executed | Not Started | In Progress | Passed | Failed | Bugs
581 | 88 | 493 | 0 | 55 | 33 | 32
Legend:
Complete
On Track
At Risk
Off Track
Overall Status: